## Task list
Date | Location | Domain | Sub-Category | Task | Responsible Team | Supervise By | Target Date | Status | Remarks
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Remove committed build log files from app folder | Self | - | 8/11/2026 | Not Started | Leftover terminal output committed with the source
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Remove 12 stray empty files from project root | Self | - | 8/12/2026 | Not Started | Empty files left by a redirected build command
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Remove the empty forms folder | Self | - | 8/13/2026 | Not Started | Folder is empty and never used
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Remove the old_bkp archived project copy | Self | - | 8/14/2026 | Not Started | Duplicate copy of the whole project; already in git history
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Move compiled frontend build out of the source tree | Self | - | 8/17/2026 | Not Started | Rebuilt on deploy, should not sit beside the source
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Add Prettier and editor configuration | Self | - | 8/18/2026 | Not Started | No config today, so everyone formats differently
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Correct the README setup steps and add a frontend guide | Self | - | 8/19/2026 | Not Started | Current steps do not work; use LOCAL_SETUP.md
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Use one env file for the database connection string | Self | - | 8/20/2026 | Not Started | API and Prisma read different env files
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Move HTML escape helper into utils and escape print title | Self | - | 8/21/2026 | Not Started | Helper duplicated in both order pages
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Add focus trap and dialog role to shared Modal | Self | - | 8/24/2026 | Not Started | Keyboard users can tab out of an open popup
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Add accessibility attributes to dropdowns and pickers | Self | - | 8/25/2026 | Not Started | Only 3 aria attributes in the whole frontend
8/10/2026 | Mahape | IT - Projects | IgniteX AI | Apply shared PageHeader and Breadcrumb on every page | Self | - | 8/26/2026 | Not Started | Used on 9 of 40 plus pages, so layouts differ
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Use record id instead of row position as list key | Self | - | 8/18/2026 | Not Started | 82 index keys can push edits onto the wrong row
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Use router navigation on logout instead of page reload | Self | - | 8/19/2026 | Not Started | Full reload on expiry looks like a crash
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Support direct URL navigation and bookmarks | Self | - | 8/20/2026 | Not Started | Typing a page URL redirects back to home
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Clean up unmatched window event listeners | Self | - | 8/21/2026 | Not Started | Three listeners added without cleanup
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Remove unsafe type casts bypassing strict mode | Self | - | 8/24/2026 | Not Started | 54 casts silently drop all type checking
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Name the specific rule in every lint suppression | Self | - | 8/25/2026 | Not Started | 79 blanket disables. Dependency: FE-16 first
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Remove the duplicate dead Sales Order page | Self | - | 8/26/2026 | Not Started | Dead 274 line copy; live page is in pages/orders
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Delete six unrouted and unused page files | Self | - | 8/27/2026 | Not Started | Not routed and not imported anywhere
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Route all Excel and PDF exports through the shared helper | Self | - | 8/28/2026 | Not Started | 10 pages bypass the helper, so formats differ
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Add a content security policy header | Self | - | 8/31/2026 | Not Started | No CSP set in nginx today
8/17/2026 | Mahape | IT - Projects | IgniteX AI | Replace inline styles with Tailwind theme classes | Self | - | 9/1/2026 | Not Started | 2167 inline styles compete with Tailwind
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Show user-facing errors in every catch block | Self | - | 9/2/2026 | Not Started | 72 catch blocks swallow failures silently
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Send the auth token once instead of three times per request | Self | - | 9/4/2026 | Not Started | Sent in body plus two headers. Needs backend change
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Merge the two routing files into a single route list | Self | - | 9/8/2026 | Not Started | Both lists drifted; some menu links are broken
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Move page-local interfaces into shared type definitions | Self | - | 9/10/2026 | Not Started | 258 local interfaces; shared types file unused
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Cap open tabs and memoise heavy table components | Self | - | 9/14/2026 | Not Started | Tabs never unmount and nothing is memoised
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Add refresh token so long sessions renew silently | Self | - | 9/16/2026 | Not Started | Hard 8 hour logout loses unsaved form entries
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Standardise every grid on the shared DataTable | Self | - | 9/18/2026 | Not Started | Used in only 6 files. Dependency: follows FE-09
8/31/2026 | Mahape | IT - Projects | IgniteX AI | Adopt React Query for server data fetching | Self | - | 9/22/2026 | Not Started | 256 useEffect blocks repeat the same logic
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Fix wrong permission code on Metal Master | Self | - | 9/17/2026 | Not Started | Page uses the Component Master code by mistake
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Disable source maps in production build | Self | - | 9/22/2026 | Not Started | Deployed map files expose the full source code
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Pass menu code to permission hook on four admin pages | Self | - | 9/25/2026 | Not Started | Hook grants all rights when the code is missing
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Add page rights check to the route guard | Self | - | 9/30/2026 | Not Started | Guard checks login only, not page permission
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Add rights checks to all remaining pages | Self | - | 10/5/2026 | Not Started | 22 pages open by URL with no rights check
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Add a global error boundary | Self | - | 10/8/2026 | Not Started | One crash blanks the screen and loses work
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Move auth token from localStorage to httpOnly cookie | Self | - | 10/13/2026 | Not Started | Any page script can read the token today
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Fix failing migration and add seed data step | Self | - | 10/16/2026 | Not Started | A fresh database cannot be created at all
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Add ESLint configuration so lint script runs | Self | - | 10/21/2026 | Not Started | Lint fails today as no config exists. Blocks FE-17
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Add CI pipeline to build and lint on every push | Self | - | 10/26/2026 | Not Started | Nothing builds or lints automatically
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Upgrade end of life packages | Self | - | 10/29/2026 | Not Started | ESLint 8 is past end of life, no security fixes
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Add automated tests for login, rights and one master screen | Self | - | 11/3/2026 | Not Started | No tests exist; 50 screens checked by hand
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Create an API service layer per module | Self | - | 11/6/2026 | Not Started | 331 API calls sit inside page files
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Build one shared MasterGrid for all 25 master screens | Self | - | 11/11/2026 | Not Started | Highest leverage; removes about 30000 lines
9/14/2026 | Mahape | IT - Projects | IgniteX AI | Split the five page files over 2000 lines | Self | - | 11/16/2026 | Not Started | Dependency: follows the FE-09 master grid