## Task List
Sr. No. | Date | Location | Domain | Sub-Category | Phase | Ref ID | Module / Page | Task | What To Change | Responsible Team | Supervise By | Target Date | Status | Remarks
1 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-39 | Repository - app folder | Remove committed build log files | Delete vite_out.txt and vite_err.txt from the app folder and add log files to .gitignore so they cannot be committed again. | Self | - | 8/11/2026 | Not Started | Priority: Low ¦ Risk: None ¦ Review Sheet Sr. 39
2 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-41 | Repository - root folder | Remove stray files from project root | Delete the accidental files named CACHED, ERROR, exporting, reading, writing, [api, [app], [internal] left behind by a redirected build command. | Self | - | 8/12/2026 | Not Started | Priority: Low ¦ Risk: None ¦ Review Sheet Sr. 41
3 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-43 | app/src/forms | Remove the empty forms folder | The folder is empty and misleads anyone reading the source layout. Delete it. | Self | - | 8/13/2026 | Not Started | Priority: Low ¦ Risk: None ¦ Review Sheet Sr. 43
4 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-42 | Repository - old_bkp | Remove the old backup folder | Confirm the old copy is safely in version history, then delete old_bkp so searches stop returning duplicate results. | Self | - | 8/14/2026 | Not Started | Priority: Low ¦ Risk: None ¦ Review Sheet Sr. 42
5 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-40 | Repository - frontend folder | Move build output out of the source tree | Stop committing the compiled bundle. Generate it during deployment instead and add the output folder to .gitignore. | Self | - | 8/17/2026 | Not Started | Priority: Low ¦ Risk: Low ¦ Review Sheet Sr. 40
6 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-44 | Whole project | Add Prettier and editor configuration | Add .prettierrc and .editorconfig matching the current code style, then format once in a single separate commit so it does not mix with real changes. | Self | - | 8/18/2026 | Not Started | Priority: Low ¦ Risk: Low ¦ Review Sheet Sr. 44
7 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-46 | Documentation | Correct the README setup steps | Replace the setup section with the working sequence already proven in LOCAL_SETUP.md, and add a short frontend guide covering folder layout and the tab system. | Self | - | 8/19/2026 | Not Started | Priority: Low ¦ Risk: None ¦ Review Sheet Sr. 46
8 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-36 | Backend env files | Use one env file for the database URL | The API reads .env.local and Prisma reads .env, so they can point at different databases. Consolidate to one file or add a startup check that warns when they differ. | Self | - | 8/20/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 36
9 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-38 | Sales Order, Purchase Order - print view | Move HTML escape helper into utils | The same escape function is copied into both order pages. Move it to utils/helpers.ts, import it in both, and escape the print window title as well. | Self | - | 8/21/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 38
10 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-28 | Shared Modal component | Add focus trap and dialog role to modal | Add role="dialog", aria-modal and focus trapping to the shared Modal. Escape already works. One component, so every popup benefits. | Self | - | 8/24/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 28
11 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-27 | Whole application | Add accessibility attributes to shared components | Add aria labels and keyboard handling to the shared dropdown, column picker and action buttons. Only 3 aria attributes exist across the whole frontend today. | Self | - | 8/25/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 27
12 | 8/10/2026 | Mahape | IT - Projects | IgniteX AI | Phase 1 | FE-34 | All pages | Apply shared PageHeader and Breadcrumb everywhere | PageHeader is on 9 pages and Breadcrumb on 3 out of 40+. Roll both out so page headings and navigation look the same on every screen. | Self | - | 8/26/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 34
13 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-29 | All list pages | Use record id as the list key | Replace the 82 places using row position as the React key with the record id from the database. Position keys cause edits to land on the wrong row after sorting or deleting. | Self | - | 8/18/2026 | Not Started | Priority: Medium ¦ Risk: Medium ¦ Review Sheet Sr. 29
14 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-33 | Login and session | Use router navigation on logout | Replace the full browser reload on session expiry with router navigation, so logging out does not look like a crash to the user. | Self | - | 8/19/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 33
15 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-31 | AdminLayout - navigation | Support direct URL navigation | When a valid route loads without an open tab, open the tab automatically instead of redirecting to home. Bookmarks and browser refresh currently do not work. | Self | - | 8/20/2026 | Not Started | Priority: Medium ¦ Risk: Medium ¦ Review Sheet Sr. 31
16 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-37 | Various components | Clean up remaining event listeners | There are 49 places adding window listeners and 46 removing them. Review the three unmatched ones and add the missing cleanup. | Self | - | 8/21/2026 | Not Started | Priority: Medium ¦ Risk: Low ¦ Review Sheet Sr. 37
17 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-30 | All pages | Remove unsafe type casts | Replace the 54 as never and as unknown as casts with correct types, starting with the repeated form resolver casts. These spots silently lose all type checking. | Self | - | 8/24/2026 | Not Started | Priority: Medium ¦ Risk: Medium ¦ Review Sheet Sr. 30
18 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-17 | All pages | Name the rule in every lint suppression | Replace the 79 bare eslint-disable-next-line comments with the specific rule being disabled, and remove the ones no longer needed. Do this after the ESLint config exists. | Self | - | 8/25/2026 | Not Started | Priority: High ¦ Risk: Low ¦ Review Sheet Sr. 17
19 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-23 | Sales Order | Remove the duplicate Sales Order page | Confirm nothing imports pages/sales/SalesOrderPage.tsx (274 lines, dead), then delete it. The live page is pages/orders (2691 lines). | Self | - | 8/26/2026 | Not Started | Priority: High ¦ Risk: Low ¦ Review Sheet Sr. 23
20 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-24 | Masters, Reports, Inventory | Delete unused page files | Delete CategoryMaster, ProductMaster, PartyMaster, ComponentItem, SalesReport and StockLedger pages. All six are unrouted and unimported. | Self | - | 8/27/2026 | Not Started | Priority: High ¦ Risk: Low ¦ Review Sheet Sr. 24
21 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-22 | All pages | Route exports through the shared helper | Ten pages write their own Excel export instead of using the helper in utils, so column names and formats differ. Move them all onto the shared helper. | Self | - | 8/28/2026 | Not Started | Priority: High ¦ Risk: Medium ¦ Review Sheet Sr. 22
22 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-35 | Deployment - nginx | Add a content security policy header | Add a CSP header to nginx.conf limiting scripts and styles to the app own origin. Frame and sniffing headers are already set. | Self | - | 8/31/2026 | Not Started | Priority: Medium ¦ Risk: Medium ¦ Review Sheet Sr. 35
23 | 8/17/2026 | Mahape | IT - Projects | IgniteX AI | Phase 2 | FE-26 | All pages | Replace inline styles with Tailwind | Move brand colours into the Tailwind theme and convert the 2167 inline style blocks to classes. Start with shared components, then work page by page. | Self | - | 9/1/2026 | Not Started | Priority: Medium ¦ Risk: Medium ¦ Review Sheet Sr. 26
24 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-14 | All pages | Handle errors in every catch block | Show a toast message in the 72 catch blocks that are currently empty or comment-only, so failures are visible to the user instead of disappearing silently. | Self | - | 9/2/2026 | Not Started | Priority: High ¦ Risk: Medium ¦ Review Sheet Sr. 14
25 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-32 | Login and session | Send the auth token only once | The token is attached three times per request, in the body and two headers. Send it in the Authorization header only and update the backend to match. | Self | - | 9/4/2026 | Not Started | Priority: Medium ¦ Risk: High ¦ Review Sheet Sr. 32
26 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-13 | Routing | Merge the two routing files into one | AppRoutes.tsx and routeRegistry.ts both map URLs by hand and have drifted. Build one route list both read from, and fix the Finding Master path mismatch and the missing slash on the Workflow Configuration menu URL. | Self | - | 9/8/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 13
27 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-12 | All pages | Move to shared type definitions | Move the 258 page-local interfaces into types/index.ts and import them, so a database column change surfaces every affected file at compile time. | Self | - | 9/10/2026 | Not Started | Priority: High ¦ Risk: Medium ¦ Review Sheet Sr. 12
28 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-18 | AdminLayout - tab system | Limit open tabs and memoise tables | Cap the number of open tabs, unmount the oldest, and add React.memo to the heavy table components. Nothing is memoised today and tabs are never unmounted. | Self | - | 9/14/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 18
29 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-19 | Login and session | Add a refresh token for long sessions | Add silent session renewal plus a warning before expiry, so a user filling a long order form is not logged out and does not lose the entry. | Self | - | 9/16/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 19
30 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-21 | All list pages | Standardise on the shared DataTable | The shared table exists but is used in only six files, four of which are dead. Fold it into the new master grid rather than maintaining two table implementations. | Self | - | 9/18/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 21
31 | 8/31/2026 | Mahape | IT - Projects | IgniteX AI | Phase 3 | FE-20 | All pages | Adopt a data fetching library | Introduce React Query so caching, retries, loading and error states are handled once instead of hand written across 256 useEffect blocks. | Self | - | 9/22/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 20
32 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-04 | Metal Master | Fix the wrong permission code | Metal Master reads rights using the Component Master menu code. Point it at its own code and audit every page for the same copy-paste error. Small change, security impact. | Self | - | 9/17/2026 | Not Started | Priority: Critical ¦ Risk: Low ¦ Review Sheet Sr. 4
33 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-05 | Build output | Turn off source maps for production | Set sourcemap to false for production builds in vite.config.ts and delete the existing .map files from the deployed folder. They currently expose the full source. | Self | - | 9/22/2026 | Not Started | Priority: Critical ¦ Risk: Low ¦ Review Sheet Sr. 5
34 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-01 | Menu, Permission, Role Master, User Role Assignment | Pass menu code to the permission hook | These four pages call usePermission() with no code, and the hook returns every right as true. Pass the correct code and change the hook to deny by default when the code is missing. | Self | - | 9/25/2026 | Not Started | Priority: Critical ¦ Risk: Medium ¦ Review Sheet Sr. 1
35 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-02 | Routing - AppRoutes.tsx | Add a rights check to the route guard | The guard only checks login. Add a page rights check using the menu list loaded at login and show a Not Authorised screen when it fails. | Self | - | 9/30/2026 | Not Started | Priority: Critical ¦ Risk: High ¦ Review Sheet Sr. 2
36 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-03 | 22 routed pages | Add rights checks to all remaining pages | Add usePermission with the correct menu code to the 22 pages that have none, including User Management, Mail Config, ERP Config and Audit Logs, and hide action buttons when the right is false. | Self | - | 10/5/2026 | Not Started | Priority: Critical ¦ Risk: High ¦ Review Sheet Sr. 3
37 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-07 | Whole application | Add a global error boundary | Wrap the main content area in AdminLayout with an error boundary showing a friendly message and reload option, so one crash no longer blanks the whole screen. | Self | - | 10/8/2026 | Not Started | Priority: Critical ¦ Risk: Medium ¦ Review Sheet Sr. 7
38 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-06 | Login and session | Move the auth token out of localStorage | Move the token to an httpOnly cookie set by the server so page scripts cannot read it. Coordinate with the backend and do this together with the single-header change. | Self | - | 10/13/2026 | Not Started | Priority: Critical ¦ Risk: High ¦ Review Sheet Sr. 6
39 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-08 | Local environment setup | Fix database setup and add seed data | Fix the migration that inserts a menu under a parent that no migration creates, and add a seed step so a fresh database has users, menus, lookups and project_config. | Self | - | 10/16/2026 | Not Started | Priority: Critical ¦ Risk: High ¦ Review Sheet Sr. 8
40 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-16 | Whole project | Add ESLint configuration | Add an ESLint config so the existing lint script actually runs, then work through what it reports. The check has never run on this codebase. | Self | - | 10/21/2026 | Not Started | Priority: High ¦ Risk: Medium ¦ Review Sheet Sr. 16
41 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-25 | Whole project | Add a CI build pipeline | Add a pipeline that installs, builds and lints on every push, so broken code is caught before it reaches anyone else. | Self | - | 10/26/2026 | Not Started | Priority: High ¦ Risk: Low ¦ Review Sheet Sr. 25
42 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-45 | Whole project | Upgrade end-of-life packages | ESLint 8 is past end of life and several packages report deprecation warnings. Plan and test the upgrade in one controlled batch. | Self | - | 10/29/2026 | Not Started | Priority: Low ¦ Risk: Medium ¦ Review Sheet Sr. 45
43 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-15 | Whole project | Add automated tests | Add Vitest plus Playwright flows covering login, permissions and one full master screen, so regressions are caught without manually checking 50 screens. | Self | - | 11/3/2026 | Not Started | Priority: High ¦ Risk: Medium ¦ Review Sheet Sr. 15
44 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-11 | All pages | Create an API service layer | Move the 331 direct API calls out of page files into one service file per module, so backend changes are made in one place instead of across page code. | Self | - | 11/6/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 11
45 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-09 | All master screens (about 25) | Build one shared master grid component | Build a single MasterGrid covering table, search, paging, sorting, filters, export and the add/edit popup, then move all 25 pages onto it. Removes roughly 30,000 duplicated lines. | Self | - | 11/11/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 9
46 | 9/14/2026 | Mahape | IT - Projects | IgniteX AI | Phase 4 | FE-10 | Finished Goods, Finding, Sales Order, Purchase Order | Split oversized page files | Split the five files over 2000 lines into table, form and API parts. Largely falls out of the shared grid work, so schedule it immediately after. | Self | - | 11/16/2026 | Not Started | Priority: High ¦ Risk: High ¦ Review Sheet Sr. 10

## Phase Plan
Phase | Name | Tasks | Sr. Range | Window | What It Covers / Exit Criteria
Phase 1 | Minor / Cosmetic & Cleanup | 12 | 1 - 12 | 8/10/2026 to 8/26/2026 | No functional impact. Safe to ship in one batch with a smoke test.
Phase 2 | Moderate Frontend | 11 | 13 - 23 | 8/17/2026 to 9/1/2026 | Component and interaction level. Each item needs its own screen test.
Phase 3 | Functional / Business Logic | 8 | 24 - 31 | 8/31/2026 to 9/22/2026 | Touches data handling, API and state. Needs regression testing per module.
Phase 4 | Major / Critical | 15 | 32 - 46 | 9/14/2026 to 11/16/2026 | Security, architecture and multi-module work. Plan, review and test each one individually.
Total | All review points | 46 | 1 - 46 |  | Every point from the review sheet is mapped exactly once. No item combined, split or dropped.
Scope note | The review sheet was scoped as a code-quality and security audit. Pure UI issues (alignment, spacing, placeholder text, basic field validation) were deliberately excluded at the time and are therefore NOT represented here.
Gap | A separate screen-by-screen functional QA pass is still needed to capture UI and validation defects. That pass is blocked until the local database has real business data.
Sequencing | Phase 1 and 2 are safe to run in parallel with feature work. Phase 3 and 4 need a dedicated branch and regression testing per module.
Dependency | FE-16 (ESLint config) should land before FE-17 (naming lint suppressions). FE-09 (shared grid) should land before FE-10 (splitting large files) and FE-21 (shared DataTable).
Highest leverage | FE-09 - build one shared master grid. It removes about 30,000 duplicated lines and makes most Phase 3 and 4 items materially cheaper.